## above_lines_aug09_2018
flightline_c | sitename_alias | plan_id | Sortie | Notional Date | Priority | Team
| BERMS TomoSAR | https://uavsar.jpl.nasa.gov/cgi-bin/report.pl?planID=PLAN_1340_v01#summary | 1 | 2018-08-19 | red | Kasischke, Chapman, Siquiera
36000 | East Peace-Athabasca Delta, Canada | https://uavsar.jpl.nasa.gov/cgi-bin/report.pl?planID=PLAN_1346_v01#summary | 2 | 2018-08-21 | red | Larry Smith, Colin Gleason
18035 | West Peace-Athabasca Delta, Canada |  | 2 | 2018-08-21 | red | Larry Smith, Colin Gleason
5530 | North Fort Resolution, Canada |  | 2 | 2018-08-21 | yellow
16008 | Baker Creek, Canada |  | 2 | 2018-08-21 | yellow | Chapman, Siquiera
16713 | Scotty Creek, Canada | https://uavsar.jpl.nasa.gov/cgi-bin/report.pl?planID=PLAN_1350_v01#summary | 3 | 2018-08-22 | red | Quinton & Balzer teams
11703 | Kakisa Lake, Canada |  | 3 | 2018-08-22 | red | Kasischke; Laura B-C team
34809 | Kakisa Lake, Canada |  | 3 | 2018-08-22 | red | Kasischke; Laura B-C team
4006 | Fort Providence, Canada |  | 3 | 2018-08-22 | red | Kasischke; Laura B-C team
35302 | Behcho |  | 3 | 2018-08-22 | red | Laura B-C team
16008 | Baker Creek, Canada |  | 3 | 2018-08-22 | red | Chapman, Siquiera
23602 | Wolf Creek, Canada | https://uavsar.jpl.nasa.gov/cgi-bin/report.pl?planID=PLAN_1348_v01#summary | 4 | 2018-08-24 | green | contact Mike Schmidt??
30806 | Kluane Lake, Canada |  | 4 | 2018-08-24 | green
31040 | Snag Yukon to Northway AK |  | 4 | 2018-08-24 | red | Schaefer "Scottie Creek"
10204 | Delta Junction Greeley |  | 7 | 2018-08-28 | yellow | Schaefer "DJ sites a, b, c"
30407 | Delta Junction to Fairbanks |  | 7 | 2018-08-28 | yellow | Schaefer "Birch Lake"
3111 | Ivotuk Legacy Line | https://uavsar.jpl.nasa.gov/cgi-bin/report.pl?planID=PLAN_1322_v02#summary | 5 | 2018-08-26 | green
34509 | Atqasuk Legacy Line |  | 5 | 2018-08-26 | green
15018 | Barrow Legacy Line |  | 5 | 2018-08-26 | red
4603 | Inigok North Slope |  | 5 | 2018-08-26 | green
16405 | Anaktuvuk Burn Scar West |  | 5 | 2018-08-26 | red | Rocha
34408 | Anaktuvuk Burn Scar East |  | 5 | 2018-08-26 | red | Rocha
18519 | Deadhorse Legacy Line |  | 5 | 2018-08-26 | red | Mack; Laura B-C
5300 | Toolik LTER |  | 5 | 2018-08-26 | red | Mack
20026 | Coldfoot Legacy Line |  | 5 | 2018-08-26 | yellow | Sarah Sackett (27th)
9114 | South Denali, AK | https://uavsar.jpl.nasa.gov/cgi-bin/report.pl?planID=PLAN_1320_v02#summary | 6 | 2018-08-27 | red | Meghan Taylor, Schaefer
9115 | Denali NEON EML, Alaska |  | 6 | 2018-08-27 | red | Meghan Taylor, Schaefer
3603 | Bonanza Creek LTER |  | 6 | 2018-08-27 | yellow | Douglas, Kane, Schaefer
3604 | Bonanza Creek LTER |  | 6 | 2018-08-27 | yellow | Douglas, Kane, Schaefer
4707 | Fort Yukon |  | 6 | 2018-08-27 | red
21609 | Yukon Flats East |  | 6 | 2018-08-27 | red
21508 | Yukon Flats West |  | 6 | 2018-08-27 | red
12227 | TomoSAR reference line 41K |  | 6 | 2018-08-27 | yellow | Schaefer "DJ sites a, b, c"
30221 | TomoSAR reference line 41K |  | 6 | 2018-08-27 | yellow | Schaefer "DJ sites a, b, c"
101 | Delta Junction NEON site |  | 6 | 2018-08-27 | yellow | Schaefer "DJ sites a, b, c"
32608 | Snake River, Alaska | https://uavsar.jpl.nasa.gov/cgi-bin/report.pl?planID=PLAN_1349_v01#summary | 7 | 2018-08-28 | green
26905 | YK Delta A |  | 7 | 2018-08-28 | green
26906 | YK Delta B |  | 7 | 2018-08-28 | green
1813 | YK Delta Chevak |  | 7 | 2018-08-28 | green
4215 | Innoko Flats |  | 7 | 2018-08-28 | green
8911 | Poorman, Alaska |  | 7 | 2018-08-28 | green
30204 | Tok to Delta Junction |  | 7 | 2018-08-28 | yellow | Schaefer TBD
5529 | Dempster Highway Fort McPherson | https://uavsar.jpl.nasa.gov/cgi-bin/report.pl?planID=PLAN_1324_v02#summary | 8 | 2018-08-30 | red
1703 | Inuvik to Tuk Highway |  | 8 | 2018-08-30 | red | Aaron Berg
25702 | Aklavik Highway |  | 8 | 2018-08-30 | red | Aaron Berg
20705 | Old Crow Flats |  | 8 | 2018-08-30 | red | Kevin Turner
24401 | Old Crow Airport |  | 8 | 2018-08-30 | green
25516 | Huslia AK Legacy Line | https://uavsar.jpl.nasa.gov/cgi-bin/report.pl?planID=PLAN_1323_v01#summary | 9 | 2018-08-31 | green
25517 | Koyuk AK Legacy Line |  | 9 | 2018-08-31 | green
32519 | Council NGEE Legacy Line |  | 9 | 2018-08-31 | red
4806 | Teller NGEE |  | 9 | 2018-08-31 | red
8502 | Kougarok Legacy Line |  | 9 | 2018-08-31 | green
3001 | Ambler Legacy Line |  | 9 | 2018-08-31 | green
28508 | Noatak, Alaska |  | 9 | 2018-08-31 | green
Note on C1: Peter Griffith: always check the UAVSAR calendar for the latest schedule and flight plans https://uavsar.jpl.nasa.gov/science/calendar.html
Note on C2: Peter Griffith: not final version
Note on C49: Peter Griffith: not final version