## Slide 1
ASTM-10 closing thoughts
Quick thoughts on things we’ve done well thus far (from a ~30k ft / 10 km perspective)
- WG efforts (coordinating across & leveraging thematically related projects)
- Cross-WG synthesis science (even more better)
- Modeling / TBMs (coordinating & benchmarking via iLaMB, etc)
These all take effort beyond individual proposed projects but it’s where the payoff is..
More broadly:
- CCEO support, including planning, tracking, HPC, infrastructure, safety, etc etc.
- Collaboration with Management agencies (NPS, F&W, etc)
- Coordination with research partners, including Canadian programs & projects

## Slide 2
Things we could (or perhaps could) have done better
- Coordination with Arctic Colors & SnowEx
  This is not for lack of trying.. but earlier would have been better (Phase-1 or 2 as opposed to Phase-3)
- Airborne data processing
  LVIS quite good
  SAR pretty good (but simultaneous L & P band never quite got there)
  AVIRIS okay (but still processing fundamental BRDF corrections in Phase-3)
ASTM-10 closing thoughts
- Working with communities / indigenous groups (challenging / some success).
  It was a different time when ABoVE kicked off but we made efforts early on.
- Early career & DEI.. maybe pretty good? We’ve tried to be on top of this..
We still have a year+ to go in Phase-3
+ some of these can be addressed via follow-on value-added efforts